Project Planning Phase

Project Planning Template – Import Data using Transform Maps (Spreadsheet)

| Date | 04 October 2026 |
| --- | --- |
| Team ID | To be filled |
| Project Name | Import Data using Transform Maps (Spreadsheet) |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

The following product backlog divides the ServiceNow spreadsheet data-import project into manageable user stories and tasks.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Spreadsheet & Import Set Preparation | USN-1 | As a ServiceNow user, I can prepare a structured employee spreadsheet with required fields and valid data so that it can be imported correctly. | 3 | High | To be filled |
| Sprint-1 | Spreadsheet & Import Set Preparation | USN-2 | As a ServiceNow user, I can load the spreadsheet into an Import Set table so that the source data is available as staging data. | 2 | High | To be filled |
| Sprint-2 | Transform Map Configuration | USN-3 | As a ServiceNow user, I can create a Transform Map and select the appropriate target table so that source data can be transformed into target records. | 3 | High | To be filled |
| Sprint-2 | Transform Map Configuration | USN-4 | As a ServiceNow user, I can map spreadsheet source fields to the correct target fields so that employee information is transferred accurately. | 2 | High | To be filled |
| Sprint-3 | Transformation & Record Creation | USN-5 | As a ServiceNow user, I can execute the transform process so that valid employee records are created in the target table. | 3 | High | To be filled |
| Sprint-3 | Transformation & Record Creation | USN-6 | As a ServiceNow user, I can review transform results and identify rejected or incorrect records so that data issues can be corrected. | 2 | Medium | To be filled |
| Sprint-4 | Validation & Documentation | USN-7 | As a ServiceNow user, I can validate imported employee records against the spreadsheet so that data integrity is maintained. | 3 | High | To be filled |
| Sprint-4 | Validation & Documentation | USN-8 | As a project team member, I can document the complete import, mapping, transformation, and verification process for future use. | 2 | Medium | To be filled |

Project Tracker, Velocity & Burndown Chart (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 5 | 5 Days | 06 Oct 2026 | 10 Oct 2026 | 5 | 10 Oct 2026 |
| Sprint-2 | 5 | 5 Days | 12 Oct 2026 | 16 Oct 2026 | 5 | 16 Oct 2026 |
| Sprint-3 | 5 | 5 Days | 19 Oct 2026 | 23 Oct 2026 | 5 | 23 Oct 2026 |
| Sprint-4 | 5 | 5 Days | 26 Oct 2026 | 30 Oct 2026 | 5 | 30 Oct 2026 |

Velocity:

For this project, the team plans 20 story points across 4 sprints. Each sprint contains 5 story points and has a planned duration of 5 days. Average velocity per sprint = 20 ÷ 4 = 5 story points/sprint. Average daily velocity = 5 ÷ 5 = 1 story point/day.

Burndown Chart:

A burndown chart shows the amount of project work remaining against time. For this project, the planned remaining story points decrease from 20 to 0 as the four sprints are completed.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

| Sprint / Day | Planned Story Points Remaining | Work Completed |
| --- | --- | --- |
| Project Start | 20 | 0 |
| End of Sprint-1 | 15 | 5 |
| End of Sprint-2 | 10 | 10 |
| End of Sprint-3 | 5 | 15 |
| End of Sprint-4 | 0 | 20 |

Project Objective: Import structured employee data from an external spreadsheet into ServiceNow using an Import Set and Transform Map, then verify the transformed records for accuracy and data integrity.

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts